AccessPDF

Project Roadmap

v0.1  |  2026

# Guiding Principles

- Ship something useful fast — a working alt text generator is more valuable than a perfect full suite

- Don't break PDFs — safety and idempotency above all else

- Make it easy to contribute — good docs, clear module boundaries, fast tests

- Be honest about limitations — the tool reports what it couldn't fix, not just what it did

# Phase 0: Foundation (Weeks 1-2)

Goal: Working skeleton that contributors can build on.

| Task | Owner | Notes |
| --- | --- | --- |
| Set up repo, CI, pyproject.toml, pre-commit hooks | Core team | GitHub Actions: lint, test, type-check |
| Define core data models (AnalysisResult, RemediationResult, ProcessorResult) | Core team | Pydantic models; these are the contract between modules |
| Implement PDFAnalyzer skeleton | Core team | pikepdf + pdfminer.six; extract metadata, images, text |
| Implement CLI skeleton with Typer | Core team | check and fix commands; reads config |
| Set up test corpus (10 public domain PDFs of varying complexity) | Core team | Commit to repo/tests/corpus/ |
| Write CONTRIBUTING.md and module interface specs | Core team | Unblock community contributions |

# Phase 1: AI Alt Text MVP (Weeks 3-5)

Goal: Working alt text generation — the core differentiator. This alone is worth shipping.

| Task | Owner | Notes |
| --- | --- | --- |
| Image extraction from PDFs (pikepdf + Pillow) | Core team | Handle JPEG, PNG, JBIG2, CCITT |
| AltTextGenerator protocol + Anthropic implementation | Core team | Isolated behind protocol for testability |
| Prompt engineering for alt text quality | Core team | Iterate with human eval; cover charts, photos, logos, decorative |
| SQLite image cache | Core team | Key: md5(image_bytes + prompt_hash) |
| Inject alt text into PDF tag structure | Core team | Hardest part — tag tree manipulation with pikepdf |
| cost-estimate CLI command | Core team | Count images, estimate tokens, show projected cost |
| pytest-vcr cassettes for API tests | Core team | Tests must run offline in CI |
| v0.1.0 release: alt text only | Core team | Announce on HN, accessibility forums |

# Phase 2: Structural Remediation (Weeks 6-10)

Goal: Fix the mechanical accessibility issues that don't require AI.

| Task | Owner | Notes |
| --- | --- | --- |
| MetadataProcessor: Title, Language, Author | Community / Core | Auto-detect language with langdetect |
| TaggingProcessor: add tag tree to untagged PDFs | Community / Core | Hard problem; start with simple single-column docs |
| HeadingProcessor: infer H1-H6 from font size | Community / Core | Heuristic-based; configurable thresholds |
| ReadingOrderProcessor: column detection + reorder | Community / Core | Use pdfminer layout analysis |
| BookmarkProcessor: generate outline from headings | Community / Core | Straightforward once headings are tagged |
| Reporter: JSON + Markdown output | Community / Core | Per-doc and aggregate batch reports |
| v0.2.0 release | Core team |  |

# Phase 3: Tables, Links & Polish (Weeks 11-15)

Goal: Reach feature completeness for v1.0.

| Task | Owner | Notes |
| --- | --- | --- |
| TableProcessor: detect tables, assign TH/TD/scope | Community / Core | Use pdfminer line detection + heuristics |
| LinkProcessor: flag non-descriptive hyperlinks | Community / Core | Report only; optional AI-powered fix |
| Color contrast reporting | Community / Core | Extract text+background colors; report issues |
| Decorative image detection heuristics | Community / Core | Size, position, aspect ratio signals |
| --no-ai flag: run all structural fixes without API | Community / Core | Important for sensitive documents |
| HTML report format with image thumbnails | Community / Core | Visual review of alt text quality |
| Performance optimization + benchmarks | Core team | Target <30s/doc |
| v1.0.0 release + blog post / HN launch | Core team |  |

# Phase 4: Ecosystem (Post v1.0)

Goals for after the initial release, to be prioritized based on community feedback.

- GitHub Action: accesspdf/action for PDF accessibility checks in CI

- Pre-commit hook

- VS Code extension for single-file remediation

- OCR integration (Tesseract) for scanned PDFs

- Local vision model support (LLaVA/Ollama) for offline/private use

- Web UI: drag-and-drop interface for non-technical users

- Integrations: SharePoint, S3, Google Drive batch connectors

# Milestones Summary

| Milestone | Target | Description |
| --- | --- | --- |
| v0.1.0 | Week 5 | AI alt text generation — core feature |
| v0.2.0 | Week 10 | Structural remediation (metadata, tags, headings, order) |
| v1.0.0 | Week 15 | Full suite: tables, links, contrast reporting, polish |
| GitHub Action | Post v1.0 | CI integration for PDF accessibility |
| Local model support | Post v1.0 | Offline/private document processing |

# Open Source Launch Strategy

- Announce v0.1 on Hacker News (Show HN), accessibility.dev, and relevant accessibility Slack/Discord communities

- Write a detailed launch post explaining the problem, the approach, and the roadmap

- Seed the issue tracker with well-scoped 'good first issue' tasks before launch

- Reach out directly to accessibility practitioners who might want to evaluate and provide feedback

- Submit to ATIA, W3C WAI, and A11y Project for community visibility