AccessPDF

Project Roadmap

v0.2  |  2026

# Guiding Principles

- Ship something useful fast — the manual alt text workflow and structural fixes are valuable even before AI is added

- No API required — every feature must have a path that works fully offline

- Don't break PDFs — safety and idempotency above all else

- Make it easy to contribute — good docs, clear module boundaries, fast tests

# Phase 0: Foundation (Weeks 1-2)

Goal: Working skeleton that contributors can build on.

| Task | Notes |
| --- | --- |
| Repo setup: CI, pyproject.toml, pre-commit (ruff, mypy) | GitHub Actions: lint, test, type-check on Python 3.10-3.12 |
| Core data models: AnalysisResult, RemediationResult, SidecarFile, AltTextEntry | Pydantic; these are the contract between all modules |
| PDFAnalyzer skeleton | pikepdf + pdfminer.six; extract metadata, images, text blocks |
| CLI skeleton (Typer): check, fix, review, generate-alt-text, providers | Stubs only; implement in later phases |
| Sidecar YAML read/write (SidecarManager) | Stable image IDs by content hash; round-trip tests |
| Test corpus: 10 public-domain PDFs of varying complexity | Committed to tests/corpus/ |
| CONTRIBUTING.md and module interface specs | Unblock community contributions before Phase 1 |

# Phase 1: Structural Remediation (Weeks 3-7)

Goal: Fix all mechanical accessibility issues that don't require AI. Fully offline.

| Task | Notes |
| --- | --- |
| MetadataProcessor: Title, Language, Author | Auto-detect language with langdetect |
| TaggingProcessor: add tag tree to untagged PDFs | Start with single-column; flag complex layouts |
| HeadingProcessor: infer H1-H6 from font size | Configurable thresholds |
| ReadingOrderProcessor: column detection + reorder | pdfminer layout analysis |
| BookmarkProcessor: generate outline from headings | Straightforward once headings are tagged |
| Reporter: JSON + Markdown output | Per-doc and aggregate batch reports; exit codes |
| accesspdf fix and accesspdf check fully working |  |
| v0.1.0 release | Announce: HN, accessibility.dev, a11y Slack communities |

# Phase 2: Manual Alt Text Workflow (Weeks 8-10)

Goal: Complete, polished manual alt text authoring — no AI required. This is the core workflow for academic and privacy-sensitive use cases.

| Task | Notes |
| --- | --- |
| Image extraction into sidecar (SidecarManager) | All images extracted on first fix run; stable IDs |
| accesspdf review: Textual TUI | ImagePanel, AltTextEditor, StatusBar, filter views |
| Terminal image rendering: sixel + block char fallback | Graceful degradation; --no-images flag |
| Keyboard shortcuts: approve, skip, mark decorative, navigate | Optimise for throughput; target >30 images/min |
| Session resume: continuous sidecar saves | Safe to Ctrl+C and continue later |
| accesspdf fix --alt-text <sidecar>: inject approved alt text | Decorative images marked as artifacts |
| Report: alt text status per image (approved/needs_review/decorative/missing) |  |
| v0.2.0 release | Announce with focus on academic / no-API use case |

# Phase 3: AI Alt Text (Weeks 11-14)

Goal: Add AI-assisted draft generation on top of the manual workflow. AI drafts feed into the same review TUI.

| Task | Notes |
| --- | --- |
| AltTextGenerator protocol + provider implementations | Anthropic, OpenAI, Gemini, Ollama |
| accesspdf generate-alt-text command | Writes AI drafts to sidecar; never overwrites approved entries |
| SQLite cache: md5(image) + provider + model + prompt | Avoid redundant API calls across documents |
| accesspdf providers command | Check API key present, Ollama reachable, etc. |
| accesspdf cost-estimate command | Count images, estimate tokens, show projected cost |
| TUI: diff view for AI draft vs edited text | Help reviewers see what they changed |
| pytest-vcr cassettes for all cloud providers | CI must run fully offline |
| Prompt engineering + quality benchmark | Evaluate across image types; publish results in docs |
| v0.3.0 release |  |

# Phase 4: Tables, Links & Polish (Weeks 15-18)

Goal: Feature completeness for v1.0.

| Task | Notes |
| --- | --- |
| TableProcessor: detect tables, TH/TD/scope | pdfminer line detection + heuristics |
| LinkProcessor: flag non-descriptive hyperlinks | Report only in v1 |
| Color contrast reporting | Extract text+background colors; flag issues |
| HTML report with image thumbnails | Visual review of alt text quality without TUI |
| Performance optimisation + benchmarks | Target <30s/doc excl. API |
| v1.0.0 release + blog post / HN launch |  |

# Phase 5: Ecosystem (Post v1.0)

- GitHub Action: accesspdf/action for PDF accessibility checks in CI

- Pre-commit hook

- Web-based review UI (Flask) — alternative to TUI for non-technical users

- OCR integration (Tesseract) for scanned PDFs

- HuggingFace Transformers provider (no Ollama required)

- Hybrid AI mode: local model by default, escalate to cloud for low-confidence images

- SharePoint, S3, Google Drive batch connectors

# Milestones Summary

| Milestone | Target | Key Feature |
| --- | --- | --- |
| v0.1.0 | Week 7 | Structural remediation — fully offline, no AI |
| v0.2.0 | Week 10 | Manual alt text workflow + TUI review |
| v0.3.0 | Week 14 | AI alt text generation (all providers) |
| v1.0.0 | Week 18 | Tables, links, contrast, polish — full suite |
| GitHub Action | Post v1.0 | CI/CD integration |
| Web review UI | Post v1.0 | Lower-friction alt text review for non-devs |